## Production Plan
Priority | Task Category | Task | Date Added | Due Date | Assigned To | High Est. (In Hours) | Low Est. (In Hours) | Actual Time Taken | Status | Notes
High | Setup | Github repo | 2025-11-07 | [5 empty] | Done
High | Setup | Trello | 2025-11-07 | [5 empty] | Done
High | Research | Find food data API to integrate into app | 2025-11-03 | [5 empty] | Done
Medium | Research | React Native for development (iOS/Android) | 2025-11-07 | [5 empty] | Done
Medium | Research | Firebase for entire backend | 2025-11-07 | [5 empty] | Done
Low | Design | Finalize wireframes/design in Figma | 2025-11-07 | [5 empty] | Done
Low | Front-end | Convert Figma screens to code | 2025-11-07 | [5 empty] | Done
Low | Front-end | Implement consistent styling elements (theme, navbar, etc) | 2025-11-07 | [5 empty] | Done
Low | Back-end | Setup Firebase | 2025-11-07 | [5 empty] | Done
Low | Back-end | Implement authentication (login/signup) | 2025-11-07 | [5 empty] | Done
Low | Back-end | Implement data API | 2025-11-07 | [5 empty] | Done
Low | Back-end | Implement loading and error handling | 2025-11-07 | [5 empty] | Done

## Page Development
Priority | Task Category | Task | Date Added | Due Date | Assigned To | High Est. (In Hours) | Low Est. (In Hours) | Actual Time Taken | Status | Notes
High | Developing | Code Log In Page | 2025-11-07 |  | Mary Adeeko | 4 | 1 | 3 | Done
High | Developing | Code the Create Your Account Page | 2025-11-07 |  | Ian Morrissey | 5 | 1 | 2 | Done
High | Developing | Code the Calendar View Page | 2025-11-07 |  | Ruby Estrada | 5 | 1 | 5 | Done
High | Developing | Code Symptom Entry Page | 2025-11-07 |  | Ruby Estrada | 5 | 1 | 5 | Done
High | Developing | Code Home Page | 2025-11-07 |  | Prapti Pyakurel | 3 | 1 |  | Done
High | Developing | Code Settings Page | 2025-11-07 |  | Mary Adeeko | 5 | 2 |  | Done
High | Developing | Code Log Your Meal Page | 2025-11-07 |  | Ian Morrissey | 5 | 1 |  | Done
High | Developing | Code Notification Sound Page | 2025-11-07 |  | Oyindamola Bade-Ojo | 5 | 1 | 5 | Done
High | Developing | Code Log Your Meal ConfirmationPage | 2026-03-05 |  | Ian Morrissey | 1 | 1 | 1 | Done
High | Developing | Code Symptom Entry Confirmation Page | 2026-03-05 |  | Ian Morrissey | 1 | 1 | 1 | Done