## Production Plan
Priority | Task Category | Task | Date Added | Due Date | Assigned To | High Est. (In Hours) | Low Est. (In Hours) | Actual Time Taken | Status | Notes
High | Setup | Github repo | 2025-11-07 | [5 empty] | Done
High | Setup | Trello | 2025-11-07 | [5 empty] | Done
High | Research | Find food data API to integrate into app | 2025-11-03 | [5 empty] | Done
Medium | Research | React Native for development (iOS/Android) | 2025-11-07 | [5 empty] | Not Done
Medium | Research | Firebase for entire backend | 2025-11-07 | [5 empty] | Not Done
Low | Design | Finalize wireframes/design in Figma | 2025-11-07 | [5 empty] | Not Done
Low | Front-end | Convert Figma screens to code | 2025-11-07 | [5 empty] | Not Done
Low | Front-end | Implement consistent styling elements (theme, navbar, etc) | 2025-11-07 | [5 empty] | Not Done
Low | Back-end | Setup Firebase | 2025-11-07 | [5 empty] | Not Done
Low | Back-end | Implement authentication (login/signup) | 2025-11-07 | [5 empty] | Not Done
Low | Back-end | Implement data API | 2025-11-07 | [5 empty] | Not Done
Low | Back-end | Implement loading and error handling | 2025-11-07 | [5 empty] | Not Done

## Page Development
Priority | Task Category | Task | Date Added | Due Date | Assigned To | High Est. (In Hours) | Low Est. (In Hours) | Actual Time Taken | Status | Notes
High | Developing | Coding Log In Page and Settings Page | 2025-11-07 |  | Mary Adeeko | 4 | 1 |  | Not Done
High | Developing | Code the Create Your Account Page and Log Your Meal Page | 2025-11-07 |  | Ian Morrissey | 5 | 1 |  | Not Done
High | Developing | Code the Symptom Entry Page & Calendar View Page | 2025-11-07 |  | Ruby Estrada | 5 | 1 |  | Not Done
High | Developing
High | Developing | Home Page | 2025-11-07 |  | Prapti Pyakurel | 3 | 1 |  | Not Done